STITCH

AI Music Workstation

—

Development Roadmap

Phases 1–3: Lyric Alignment, Musical Range & Stem Mixing

| 3 Development Phases | 22 Planned Features | ~6wk Estimated Timeline |
| --- | --- | --- |

Confidential working document — April 2026

Contents

| 01 | Vision and Principles | 3 |
| --- | --- | --- |
| 02 | Where We Are Now | 4 |
| 03 | The Keystone: Alignment Layer | 5 |
| 04 | Phase 1 — Lyric Alignment & Precision | 6 |
| 05 | Phase 2 — Musical Range & Structure | 9 |
| 06 | Phase 3 — Stem Mixer Console | 12 |
| 07 | Full Feature Backlog | 14 |
| 08 | Dependency Map | 16 |
| 09 | Technical Stack | 17 |
| 10 11 | Risk Register Full Dream List | 18 19 |

01  Vision and Principles

What Stitch is becoming

Stitch started as a prompt-in, music-out tool. The roadmap ahead transforms it into a composer’s workstation — a system where the human is in genuine creative control at every level of the music, not just at the front door.

The three phases below address the highest-priority gaps between where Stitch is now and where it needs to be to serve serious creative work.

Guiding principles

| Component | What it does |
| --- | --- |
| Offline first | Every feature must work without internet after initial model download. No API keys, no subscriptions, no cloud dependency. |
| Fallback always | Every new capability must degrade gracefully. If a model isn’t downloaded, the previous behaviour continues without crashing. |
| Transparency | The user should always be able to see what the AI produced and why — lyrics, alignment, confidence scores. No black boxes. |
| Composability | Features should build on each other. The alignment layer unlocks section repair, which unlocks bar-level editing. Design accordingly. |
| VRAM respect | Stitch shares GPU memory with ACEStep. Any new model must be CPU-side or use a small, bounded GPU budget. |

02  Where We Are Now

Capabilities as of April 2026

| Component | What it does |
| --- | --- |
| Text-to-music | Full song generation from style prompt + lyrics prompt via ACEStep 1.5. |
| Cover / restyle | Transforms an uploaded audio file into a new style while preserving structure. |
| Vocal + backing | Generates instrumental backing for a dry vocal upload. |
| Repair | Region or full-file audio repair with a hint prompt. |
| Stem separation | Demucs-powered separation into vocals, drums, bass, other. |
| AI lyrics | Offline GGUF LLM (Qwen2.5 1.5B/3B/7B) with Creativity and Topic Adherence sliders. |
| Presets | Save and recall full parameter sets per mode. |
| History | Persistent session history with starring and sorting. |

|  | The gap Stitch generates music but cannot yet show the user what was generated, where it sits in time, whether the words were sung correctly, or give control over specific moments. The features below close that gap systematically. |
| --- | --- |

03  The Keystone: The Alignment Layer

Why alignment unlocks everything else

The alignment layer is the single most leveraged investment in this roadmap. It is not a visible feature itself — it is the engine that makes a dozen other features possible.

What it does:

- Takes the generated audio and the generated lyrics as input.

- Runs forced alignment (whisper-timestamped or wav2vec2-based) to produce a word-level timestamp map.

- Scores each word with a confidence value — how clearly it was sung vs. the intended text.

- Stores the result as a lightweight JSON sidecar alongside each generated audio file.

What it enables:

| Component | What it does |
| --- | --- |
| Lyric timeline view | Display lyrics scrolling word-by-word in sync with playback. |
| Confidence flagging | Highlight unclear words in red before the user even listens. |
| Single-word repair | Know exactly which time span to mask for targeted regeneration. |
| Section timestamps | Know where Verse 1 ends and the Chorus begins for section-level regeneration. |
| Lyric lock / unlock | Pin specific lines so regeneration cannot drift them. |
| Annotation anchoring | Attach timestamped notes to specific moments in the audio. |
| Loop extraction | Detect and export repeating musical phrases by time span. |

|  | Implementation note whisper-timestamped (an offline wrapper around OpenAI Whisper) is the recommended tool. It produces word-level start/end times and per-word probabilities. The base or small Whisper model runs comfortably on CPU in 5–15 seconds per song. No GPU required, no internet required after the one-time model download (~150 MB). |
| --- | --- |

| PHASE 1 | Lyric Alignment & Precision See exactly what was sung, fix exactly what wasn’t. |
| --- | --- |

04  Phase 1 Detail

Goal

Transform Stitch from a generation tool into an auditable one. After this phase, the user will always know whether the AI sang what was asked, which words are unclear, and how to fix individual words without regenerating the whole song.

Feature 1.1 — Lyric Timeline View

After generation, a scrolling lyric panel appears below the waveform. Each word is highlighted as it is sung. Section headers ([Verse 1], [Chorus], etc.) appear as visual dividers.

| Component | What it does |
| --- | --- |
| Audio playback hook | The existing waveform widget fires a position signal every ~50ms. The timeline subscribes to this signal to move the highlight cursor. |
| Alignment sidecar | A JSON file stored alongside each .wav: { words: [{word, start, end, confidence}], sections: [{label, start, end}] } |
| UI component | A new LyricTimelineWidget below the ResultCard. Words displayed as inline spans, coloured by confidence. Clicking a word seeks playback to that position. |
| Rendering strategy | Pre-render word spans into a QTextEdit with QTextCharFormat colour markup. Update current-word highlight via a QTimer slot at 50ms intervals. |

Feature 1.2 — Confidence Flagging

Words with alignment confidence below a user-adjustable threshold are highlighted in amber (borderline) or red (unclear). A summary banner shows “3 unclear words detected” after generation.

| Component | What it does |
| --- | --- |
| Threshold setting | A slider in Settings → Generation: ‘Flag words below confidence [0.0–1.0]’. Default 0.6. |
| Colour coding | Confidence ≥ threshold: white. 0.4–0.6: amber highlight. < 0.4: red highlight. |
| Banner widget | A collapsible info bar above the timeline: ‘X words may be unclear — click to review’. Clicking jumps to the first flagged word. |
| No false negatives | Whisper’s confidence is word-level probability. Values below 0.5 reliably indicate mumbled, merged, or mispronounced words in practice. |

Feature 1.3 — Single-Word Repair

Right-click a flagged word in the timeline to open a context menu: ‘Repair this word’. The system masks the exact time region of that word in the audio and runs ACEStep repair mode with tight region bounds, re-singing only that word.

|  | Why this is the standout feature Suno and Udio offer no sub-song repair at all. The ability to fix a single mumbled word while keeping every other note, inflection, and instrument exactly as generated is genuinely novel in consumer AI music tools. |
| --- | --- |

| Component | What it does |
| --- | --- |
| Region extraction | Use alignment sidecar to get exact start/end seconds for the word. Add 50ms padding each side to avoid clipping. |
| Repair call | Route to existing repair_page logic with mode=REGION, region_start_sec, region_end_sec, hint_prompt set to the intended word text. |
| Audio splice | On success, splice the repaired region back into the original audio using soundfile + numpy array slicing. Save as a new variation, preserving the original. |
| Re-align | Run alignment again on the spliced result. Update the sidecar and refresh the timeline display. |

Feature 1.4 — Section-Level Regeneration

The timeline shows section dividers. Right-clicking a section header offers ‘Regenerate this section’. Only the selected section is replaced; all others are preserved.

| Component | What it does |
| --- | --- |
| Section timestamps | Pulled from the alignment sidecar’s sections array. |
| Region repair call | Same mechanism as word repair, but at section granularity. Passes the section’s lyric content as hint_prompt. |
| Crossfade | Apply a 100ms crossfade at both splice boundaries using scipy.signal to avoid clicks. |
| Locked sections | A lock icon on each section header. Locked sections are skipped by regeneration and highlighted with a subtle border. |

Phase 1 — Task Breakdown

| # | Task | Effort | Depends on |
| --- | --- | --- | --- |
| 1.1 | Add whisper-timestamped to requirements.txt + run.bat install step | 2h | None |
| 1.2 | Write alignment runner: takes audio + lyrics, returns sidecar JSON | 3h | 1.1 |
| 1.3 | Call alignment runner after every successful generation | 1h | 1.2 |
| 1.4 | Build LyricTimelineWidget (word spans, colour coding, click-to-seek) | 6h | 1.3 |
| 1.5 | Wire QTimer playback position signal into timeline highlight cursor | 2h | 1.4 |
| 1.6 | Add confidence threshold slider to Settings → Generation tab | 1h | 1.2 |
| 1.7 | Add flagged-words banner above timeline | 2h | 1.4 |
| 1.8 | Right-click context menu on words: Repair this word | 2h | 1.4 |
| 1.9 | Word repair: mask region, call repair, splice result, re-align | 5h | 1.5, 1.8 |
| 1.10 | Section dividers in timeline with lock icons | 3h | 1.4 |
| 1.11 | Section-level regeneration via repair mode | 4h | 1.9, 1.10 |

|  | Phase 1 total estimate Approximately 2–3 days of focused development. The alignment runner (1.2) is the critical path item — everything else depends on it. whisper-timestamped is well-documented and the forced alignment API is straightforward. |
| --- | --- |

| PHASE 2 | Musical Range & Structure Unlock the full palette: tempo, key, time signature, structure. |
| --- | --- |

05  Phase 2 Detail

Goal

Expose the musical parameters that ACEStep already supports but that the current UI hides. Add structure templating so the user controls the arc of a song, not just its genre. This phase dramatically expands the range of music Stitch can produce without requiring any new models.

Feature 2.1 — Tempo, Key and Time Signature

Three new controls appear in the Text prompt panel under a collapsible ‘Musical parameters’ section: a BPM slider, a key dropdown, and a time signature selector. All three pass through to GenerationParams in ACEStep.

| Component | What it does |
| --- | --- |
| BPM slider | Range 40–200 BPM, default blank (free). Snaps to common tempos (60, 80, 90, 100, 120, 140, 160) with a ‘tap’ button to set by tapping. |
| Key dropdown | 12 major + 12 minor keys (C major, A minor, etc.) plus ‘Free’. Maps to ACEStep’s key field as a string. |
| Time signature | Selector: 4/4 (default), 3/4, 6/8, 5/4, 7/8. Passed as a tag appended to the style prompt if ACEStep has no native field. |
| Persistence | Values saved into session presets alongside style prompt and lyrics. |
| API mapping | Check GenerationParams signature at runtime (as done elsewhere in _ace_worker_v15.py) and pass only fields that exist. |

Feature 2.2 — Song Structure Templating

A drag-and-drop section sequencer lets the user arrange the song before generation: add/remove/reorder sections, choose their type (Intro, Verse, Pre-Chorus, Chorus, Bridge, Outro, Instrumental break), and set a rough duration target for each.

| Component | What it does |
| --- | --- |
| Section builder UI | A horizontal row of draggable pill widgets. Each pill shows its section type and target duration. Add / remove via + and × buttons. |
| Lyric block linking | Each Verse or Bridge pill has an optional text area for its specific lyrics. Chorus pills share one lyric block by default. |
| Prompt injection | On generation, the section sequence is serialised into the lyrics field as structured tags: [Intro], [Verse 1], [Chorus], etc., with total duration distributed proportionally. |
| Mood arc per section | Each section pill has an optional ‘energy’ badge: Low / Mid / High. Gets appended to that section’s caption hint. |
| Presets | Common templates available as one-click presets: Standard Pop, Ballad, EDM build, Anthem, Film theme. |

Feature 2.3 — Negative Prompting

A ‘Not this:’ text field below the style prompt. Content entered here is appended to the style caption with exclusion language. Tested against ACEStep’s caption conditioning behaviour.

| Component | What it does |
| --- | --- |
| UI | A collapsed field under the style prompt, expanded with a ‘+ Exclusions’ link. Placeholder: ‘no piano, no autotune, no trap beat’. |
| Prompt injection | Appended as: ‘Avoid: [content]’ to the caption. ACEStep’s caption conditioning is sensitive to this phrasing in practice. |
| Saved in presets | Exclusion string persists with the preset. |

Feature 2.4 — Micro-Genre Blend Wheel

Instead of typing a free-text style prompt from scratch, a blend widget shows two or three genre slots with a proportion control between them. The combined result is auto-generated as a style prompt string.

| Component | What it does |
| --- | --- |
| Blend widget | Two genre combo boxes with a slider between them (0–100%). A third optional genre can be added. Preview shows the generated style prompt string. |
| Genre vocabulary | A curated list of ~80 genre/subgenre terms that ACEStep responds well to, built from testing. Searchable dropdown. |
| Free text fallback | A ‘Manual’ toggle switches back to the existing free-text field at any time. |
| Saved in presets | Blend ratios and genres save alongside other preset data. |

Feature 2.5 — Reference Track Style Extraction

The user drops in an audio file and Stitch analyses its musical characteristics offline, then auto-populates the BPM, key, and style prompt fields. No copying of the reference audio — only metadata extraction.

| Component | What it does |
| --- | --- |
| BPM detection | librosa.beat.beat_track() — already a dependency, no new packages needed. |
| Key detection | librosa.estimate_tuning() + chroma analysis for key estimation. Accuracy is ∼80% for tonal music. |
| Timbral description | Spectral centroid, rolloff, and zero-crossing rate mapped to descriptive adjectives (bright/dark, dense/sparse, energetic/calm) injected into the style prompt. |
| Genre suggestion | Optional: run a small offline genre classifier (will list as a future enhancement, not Phase 2 scope). |

Phase 2 — Task Breakdown

| # | Task | Effort | Depends on |
| --- | --- | --- | --- |
| 2.1 | Inspect GenerationParams for bpm/key fields; expose BPM slider in UI | 2h | None |
| 2.2 | Add key dropdown (24 options + Free) to text panel | 1h | 2.1 |
| 2.3 | Add time signature selector; inject as style prompt tag if no native field | 1h | 2.1 |
| 2.4 | Build section pill row widget (drag, add, remove, type selector) | 6h | None |
| 2.5 | Lyric block linking per Verse/Bridge pill | 3h | 2.4 |
| 2.6 | Serialise section template to structured lyrics + caption hints | 2h | 2.4, 2.5 |
| 2.7 | Add negative prompt field; wire into caption | 1h | None |
| 2.8 | Build genre blend widget (2 slots + proportion slider) | 4h | None |
| 2.9 | Build genre vocabulary list (~80 terms) from ACEStep testing | 3h | None |
| 2.10 | Add reference audio drop zone; run librosa BPM + key extraction | 3h | None |
| 2.11 | Map timbral features to style prompt adjectives | 2h | 2.10 |
| 2.12 | Save all new fields in preset system | 2h | 2.1–2.11 |

|  | Phase 2 total estimate Approximately 2–3 days. Features 2.1–2.3 are the quickest wins — they expose parameters ACEStep already supports. The section template (2.4–2.6) is the most involved UI task but produces the biggest creative range expansion. |
| --- | --- |

| PHASE 3 | Stem Mixer Console Post-generation control: mix, balance, and re-export. |
| --- | --- |

06  Phase 3 Detail

Goal

Demucs stem separation already runs inside Stitch. The stems are exported as files but there is currently no way to adjust their balance and remix without an external DAW. Phase 3 adds an inline mixing console so the user can turn down the drums, push up the bass, pan the guitar, and re-export — all without leaving the app.

Feature 3.1 — Per-Stem Volume and Pan

A StemMixer panel opens from the result card when stems are available. Shows one channel strip per stem (Vocals, Drums, Bass, Other) with a fader, a pan knob, a mute button, and a solo button.

| Component | What it does |
| --- | --- |
| Volume fader | QSlider vertical, range −48dB to +6dB, default 0dB. Mapped to linear gain via 20**(db/20). |
| Pan knob | QDial, range L100 – R100, default centre. Applied as left/right channel gain split. |
| Mute / Solo | Mute zeroes the gain for that stem. Solo mutes all others temporarily. |
| Real-time preview | A ‘Preview mix’ button renders a 10-second preview of the current mix settings using numpy/soundfile before committing to a full render. |
| State persistence | Mix settings saved per result card in the session JSON so they survive app restarts. |

Feature 3.2 — Per-Stem EQ

Each channel strip has an expandable EQ section: three bands (Low, Mid, High) with gain sliders (−12 to +12dB). Applied as a simple biquad filter chain using scipy.signal.

| Component | What it does |
| --- | --- |
| Filter design | scipy.signal.iirfilter: shelf filters for Low and High, peak filter for Mid. Pre-computed at render time, not real-time. |
| Frequency targets | Low shelf: 200Hz. Mid peak: 1kHz (adjustable). High shelf: 8kHz. Standard three-band mastering positions. |
| Gain range | −12dB to +12dB per band. A flat button resets all three to 0dB. |
| Visual feedback | A small static frequency curve graphic updates to reflect current EQ settings (SVG drawn with PySide6 QPainter). |

Feature 3.3 — Mix Render and Export

A ‘Render mix’ button combines all stem channels according to current fader, pan, and EQ settings into a final mixed stereo file. Optionally applies a light mastering pass (loudness normalisation) before export.

| Component | What it does |
| --- | --- |
| Mix engine | Load all stem WAVs as numpy arrays. Apply gain, pan, and EQ in sequence per stem. Sum to stereo. Write via soundfile. |
| Loudness normalisation | pyloudnorm: measure integrated LUFS, apply gain to reach −14 LUFS (streaming standard). Configurable target. |
| True peak limiting | Simple look-ahead limiter at −0.3 dBTP to prevent inter-sample clipping. Implemented in numpy. |
| Export formats | WAV (lossless), MP3 via ffmpeg (if available), FLAC. Format selector in the render dialog. |
| Save as new variation | Rendered mix saved as a new entry in the result list, linked to the source generation, clearly labelled ‘Custom mix’. |

Feature 3.4 — Vocal Pitch Correction (Light)

An optional step in the vocal channel strip: a gentle pitch correction pass on the vocals stem before mixing. Not heavy autotune — a transparent correction that tightens intonation without changing the character of the performance.

| Component | What it does |
| --- | --- |
| Library | pyrubberband (offline, no VRAM). Provides pitch shifting with formant preservation. |
| Correction strength | A slider: Off / Subtle / Medium / Tight. Controls the window size and correction depth of the pitch analysis. |
| Key awareness | If a key was set in Phase 2, correction snaps to scale tones. Otherwise uses chromatic correction. |
| Non-destructive | Original vocal stem always preserved. Corrected version is a new file referenced only from the mix session. |

Phase 3 — Task Breakdown

| # | Task | Effort | Depends on |
| --- | --- | --- | --- |
| 3.1 | Add ‘Open mixer’ button to ResultCard (visible when stems exist) | 1h | None |
| 3.2 | Build StemMixerPanel widget: one channel strip per stem | 5h | 3.1 |
| 3.3 | Implement fader gain + pan as numpy array transforms | 2h | 3.2 |
| 3.4 | Mute and Solo logic across channel strips | 1h | 3.2 |
| 3.5 | 10-second preview render in background thread | 3h | 3.3 |
| 3.6 | Three-band EQ per stem (scipy.signal biquad) | 3h | 3.2 |
| 3.7 | EQ frequency curve SVG visual feedback | 2h | 3.6 |
| 3.8 | Full mix render engine (numpy sum, all stems) | 2h | 3.3, 3.6 |
| 3.9 | Loudness normalisation + true peak limiter (pyloudnorm) | 2h | 3.8 |
| 3.10 | Export dialog: format selector, render progress, save as new variation | 3h | 3.8, 3.9 |
| 3.11 | Vocal pitch correction with pyrubberband | 4h | 3.2 |
| 3.12 | Persist mix settings in session JSON | 2h | 3.2 |

|  | Phase 3 total estimate Approximately 2–3 days. The core mixer (3.1–3.5) is independently releasable in about one day. EQ, mastering, and pitch correction are additive layers that can follow. No new model downloads required for any of Phase 3. |
| --- | --- |

07  Full Feature Backlog

These are the complete set of features identified for future phases. None are in scope for Phases 1–3 but all are designed to build on their foundations.

|  | DAW Direction |
| --- | --- |

| Component | What it does |
| --- | --- |
| Piano roll melody hints | Sketch a rough melodic contour; condition generation on it via ACEStep melody_hint parameter. |
| Chord progression editor | Bar-by-bar chord timeline. Map C–Am–F–G and condition the generation on that harmonic structure. |
| Stem-aware bar editing | Keep drums from variation 2, regenerate vocals from variation 4. Cross-variation stem compositing. |
| Arrangement layers | Define which instruments appear in which sections before generation. Orchestration prompt per section. |
| Humanisation controls | Timing tightness (mechanical vs. swung), velocity variation, room size — affect the feel of the performance. |
| Loop extraction | Detect and export repeating musical phrases as individual audio loops ready for use in a DAW. |

|  | Film / TV / Animation |
| --- | --- |

| Component | What it does |
| --- | --- |
| Video import + duration lock | Drop in a video; constrain generation to exact duration and optionally sync musical events to visual cuts. |
| Scene marker system | User places markers at key moments (action, emotional peak, resolution); music is conditioned to have events at those timestamps. |
| Emotional curve mapping | Draw an intensity curve over the video timeline. Generation respects the envelope. |
| Cue library mode | Generate 10–20 short variations of a theme at different energy levels — interchangeable background cues. |
| Stinger generation | Short 5–10 second punchy musical events: accent hits, comedy stings, horror swells. |
| Loop-to-cue export | From one theme: auto-generate 30s, 60s, loopable, fade-out, and sting versions as broadcast deliverables. |
| SMPTE timecode export | Embed timecode markers in exported audio for professional post-production sync. |

|  | Collaboration & Versioning |
| --- | --- |

| Component | What it does |
| --- | --- |
| Version tree | Branching version tree showing lineage of all generations, not a flat list. |
| Session snapshots | Save and restore entire session state: prompts, slider values, starred items, stems. |
| Comparison mode | A/B playback of two generations with single-keypress switching. |
| Annotation layer | Timestamped notes on any generation: ‘guitar too bright at 1:23’, ‘love this fill’. Feed back into next gen. |
| Co-writing mode | AI writes a verse, user edits, AI writes chorus constrained by that verse. Turn-based lyric building. |

|  | Advanced Post-Processing |
| --- | --- |

| Component | What it does |
| --- | --- |
| Vocal doubling | Generate tight double or harmonised part from the separated vocal stem using pitch shifting. |
| Room matching | Analyse reverb signature of a reference track and apply matched reverb to generated output. |
| Format-aware export | FLAC, OGG (game engine ready), multi-track zip, stems with BWF markers, DAW-ready folder structure. |
| Timbral reference matching | Match overall tonal character (brightness, warmth) of a reference track for sonic consistency across cues. |

|  | Intelligence Layer |
| --- | --- |

| Component | What it does |
| --- | --- |
| Emotional coherence scoring | Classifier estimates whether the music’s sonic mood matches the intended mood. Flags mismatches. |
| Prompt expansion | User types a brief idea; system suggests specific instrumentation, tempo range, key, reference artists. |
| Prompt memory | Learns which style prompts produced starred results and suggests similar language in future sessions. |
| Style vocabulary guide | In-app reference of terminology ACEStep responds well to, built from testing. |
| Live regeneration | Adjust sliders during playback; new generation queued and crossfaded in when ready. |
| Narrative arc mode | Generate a set of related pieces sharing melodic DNA that evolve over time — for albums or soundtracks. |
| Adaptive game scoring | Music responds to game state changes: branching based on tension, looping calm sections, transitioning on events. |

08  Dependency Map

How Phase 1 features unlock everything downstream.

| Alignment runner | → | Lyric timeline, confidence flags, word repair, section regeneration, annotation anchoring, loop extraction, co-writing mode |
| --- | --- | --- |
| Section timestamps | → | Section-level regeneration, mood arc per section, SMPTE export, video sync markers |
| Word repair (1.3) | → | Section repair, live regeneration, adaptive game scoring |
| BPM + key (2.1) | → | Vocal pitch correction (key-aware), chord progression editor, adaptive scoring, reference matching |
| Structure template (2.4) | → | Cue library mode, stinger generation, loop-to-cue export, narrative arc mode |
| Stem mixer (3.1) | → | Vocal doubling, room matching, format-aware export, DAW-ready output, timbral matching |
| Mix render engine (3.8) | → | All export formats, broadcast deliverables, loop-to-cue export |

09  Technical Stack

New dependencies introduced by these three phases.

| Component | What it does |
| --- | --- |
| whisper-timestamped | Word-level forced alignment. CPU-only. Base Whisper model ~150 MB. Phase 1 requirement. |
| pyloudnorm | Broadcast loudness normalisation (LUFS). CPU-only. Tiny package. Phase 3. |
| pyrubberband | High-quality pitch shifting with formant preservation. CPU-only. Phase 3 vocal correction. |
| scipy.signal | Biquad filter design for EQ. Already a transitive dependency via librosa. No new install. |
| numpy | Array-based audio mixing engine. Already installed. No new install. |
| soundfile | Multi-channel WAV I/O for stem mixing. Already installed. No new install. |

|  | VRAM impact Phases 1, 2, and 3 add zero VRAM usage. whisper-timestamped runs on CPU. The stem mixer, EQ, mastering, and pitch correction are all CPU/numpy operations. The only GPU memory user remains ACEStep itself. |
| --- | --- |

10  Risk Register

| Risk | Severity | Mitigation |
| --- | --- | --- |
| Alignment accuracy on heavily processed vocals | Medium | whisper-timestamped degrades on pitch-shifted or very reverberant vocals. Fallback: display lyrics without timing, offer manual timestamp adjustment. |
| ACEStep repair precision at word boundaries | Medium | Sub-200ms repair regions may bleed into adjacent notes. Mitigation: enforce a minimum 300ms repair window; auto-expand narrow regions. |
| whisper-timestamped install friction on Windows | Low | The package has a native C extension. Pre-built wheels exist for Python 3.10/3.11 on Windows. Add to run.bat with the same CUDA-detection logic as llama-cpp-python. |
| pyrubberband requires RubberBand native library | Low | On Windows, pyrubberband needs rubberband.dll. Bundle it in a /libs folder or fall back to librosa pitch shift if not found. |
| scipy EQ introduces audible artefacts at high gain | Low | Biquad filters at ±12dB are well-behaved. Cap the UI at ±10dB as a guard. Add a ‘reset EQ’ button prominently. |
| ACEStep GenerationParams fields differ by version | Medium | Already handled in _ace_worker_v15.py with inspect-based field detection. Apply the same pattern to all new fields (bpm, key). |

|  | Overall risk level: Low All three phases use well-established offline libraries with known Windows compatibility stories. The highest-risk item (alignment accuracy) has a complete graceful fallback that preserves current functionality. No phase requires internet access, cloud APIs, or new GPU memory. |
| --- | --- |

11  Full dream list

1. Lyric precision and alignment

This is probably your highest-ROI area right now because it directly fixes a frustrating everyday experience.

Lyric timeline view. After generation, display the lyrics scrolling in sync with the audio — word by word, aligned to the actual sung timing via forced alignment (tools like whisper-timestamped or wav2vec2 can do this offline). Right now you have no idea if the AI even sang what you asked for. This single feature transforms the tool from a black box into something you can actually audit.

Word-level confidence flagging. Run the alignment and flag any word where the transcription confidence is below a threshold — highlight it in red in the timeline. The user immediately sees exactly which words are unclear without having to listen five times.

Single-word regeneration. The flagged word is the target region. Mask that time span in the audio, use ACEStep's repair mode with a very tight region, and re-sing just that word. This is genuinely not available in Suno or Udio and would be a standout feature. The hard part is region precision — you'd need sub-half-second accuracy — but the repair page already exists, it just needs the alignment data to feed into it automatically.

Phoneme-level edit hints. Go further: if "mountain" keeps coming out as "fountain", let the user type a pronunciation hint in IPA or simple respelling ("MAO-ten") that gets prepended to the lyrics for that word.

Lyric lock/unlock per line. When regenerating, mark specific lines as locked so ACEStep can't drift them. Useful when one verse is perfect but the chorus needs another try.

2. Musical range and structure control

Section-level regeneration. Right now it's full song or nothing. The ability to say "regenerate just the bridge" while keeping everything else is enormously powerful. ACEStep's repair mode supports regions — it just needs the section timestamps from the alignment layer to target them precisely.

Tempo and key pinning. Let the user specify BPM and key/scale before generation. ACEStep supports bpm and key in its GenerationParams — they're just not exposed in the UI. A BPM slider (60–200) and a key dropdown (C major, A minor, etc.) would meaningfully expand creative control.

Time signature. 4/4 is the overwhelming default. Exposing 3/4, 6/8, 5/4 as options would unlock waltz, compound, and odd-meter feels that almost nobody else offers.

Song structure templating. Right now the structure is whatever the LLM decides. Let the user drag a sequence like [Intro] → [Verse] → [Pre-Chorus] → [Chorus] → [Verse] → [Chorus] → [Bridge] → [Chorus] → [Outro] and pin that. The lyrics gen already produces section tags — this just means honouring them structurally in the generation prompt.

Mood arc. Describe how the song should feel over time: starts melancholy, builds through the verses, explodes in the chorus, ends bittersweet. This gets passed as a per-section caption rather than one global style prompt.

Transition control. Hard cuts between sections vs. smooth crossfades vs. a specific transition style (key change, break, drum fill). This is DAW territory but maps reasonably onto prompt modifiers per section.

Micro-genre blending. "70% jazz, 30% bossa nova" or "dark pop with hints of Ennio Morricone" — a blend wheel with two or three genre slots rather than a free-text field. The style prompt is already free-text but a structured blending UI would make this discoverable.

3. DAW-direction: bar-level control

This is the most ambitious direction but also the most differentiated. Nothing on the market does this well.

Piano roll for melody hints. Let the user sketch a rough melodic contour — not note-perfect, just the shape of the vocal line — and condition the generation on it. ACEStep has a melody_hint parameter buried in its API. If it works, even loosely, it's huge.

Chord progression editor. A visual chord timeline where the user places chords bar by bar (C - Am - F - G), and the generation is conditioned on that progression. For guitarists and pianists this is the natural way to think about songs.

Stem-aware bar editing. You've already got Demucs for stem separation. Combine that with bar-level generation: "keep the drums and bass from variation 2, but regenerate the vocals and melody from variation 4." This is genuinely a new workflow that doesn't exist elsewhere.

Arrangement layers. Let users define what instruments appear in which sections. "Intro: just piano. Verse: add bass and light drums. Chorus: full band. Bridge: strip back to vocals and strings." This is essentially an orchestration prompt per section.

Humanisation controls. Sliders for timing tightness (mechanical vs. loose/swung), velocity variation, and reverb/room size. These affect the feel of the performance even if the notes stay the same.

Loop extraction. Detect and export repeating musical phrases (the hook, the drum pattern, the bass riff) as individual audio loops ready for use in a DAW. This turns Stitch's output into raw material for further production work rather than a finished file.

4. Film, TV and animation scoring

This is an underserved market and a genuinely distinct product direction.

Video import and sync. Drop in a video file, and the generated music is constrained to exactly that duration and tempo. This sounds simple but requires matching the generation to a fixed length (ACEStep's duration parameter) and optionally syncing musical events to visual events.

Scene marker system. The user places markers on the video timeline: "action starts at 0:23", "emotional peak at 1:15", "resolution at 2:40". The music generation is conditioned to have musical events at those timestamps — swells, drops, key changes. This is what professional composers do manually and nobody has automated it.

Emotional curve mapping. A line that the user draws over the video representing the emotional intensity over time. Low = quiet/sparse, high = full/intense. The generation respects that envelope. Think of it as a dynamics map for the whole piece.

Cue library mode. Generate 10 or 20 short variations of a theme — 30 seconds each, different energy levels, same melodic identity — for use as interchangeable background cues. A TV composer needs "the same music but quieter" and "the same music but more tense" as separate files they can cut between.

Stinger generation. Short punchy musical events (5–10 seconds) that accent a specific moment — a sting when a character reveals something, a comedic tuba hit, a horror swell. These are separate from the main score and need to be easy to generate in batches.

Loop-to-cue export. Generate a main theme, then automatically create: a 30s version, a 60s version, a loopable version, a fade-out version, and a sting — all from the same musical material. Broadcast standard deliverables in one click.

SMPTE/timecode awareness. For professional post-production, the audio needs to lock to timecode. Export with embedded timecode markers.

5. Collaboration and versioning

Version tree. Right now results are a flat list. A branching version tree — where you can fork from any specific generation, make changes, and see the lineage — would make iterative refinement much more legible. "I liked variation 3 from session 2, and I want to try the chorus from that but with a different bridge."

Session snapshots. Save the entire state of a session: prompts, slider values, which variations were starred, stems that were exported. Recall it exactly later. Right now nothing persists between runs except the audio files.

Comparison mode. Play two generations side by side, A/B switching with a single keypress, rather than hunting through result cards.

Annotation layer. Let the user leave timestamped notes on a generation: "the guitar here is too bright", "love this drum fill at 1:23", "chorus feels rushed." These notes feed back into the next generation as negative/positive prompts.

6. Post-processing pipeline

Mastering chain. A simple one-click mastering pass after generation: loudness normalisation to a target LUFS (streaming standard), high-shelf air boost, gentle limiting. Offline, using pyloudnorm and a simple EQ. Most AI music tools skip this and the output sounds quiet and unpolished compared to commercial tracks.

Stem mixing console. Once stems are separated, expose a simple mixer: per-stem volume, pan, and a basic EQ. Let the user turn down the drums, push up the bass, and re-export. This is a 20-minute implementation that adds enormous value.

Vocal doubling. Take the separated vocal stem and generate a tight double or harmonised part. This is achievable with pitch-shifting tools (librosa, pyrubberband) and would make the vocals feel more produced.

Pitch correction on vocals. Run the vocal stem through a pitch correction step (auto-tune style, light touch) before re-mixing. Tools like psola or world can do this offline.

Room and reverb matching. If the user provides a reference track, analyse its reverb signature and apply a matched reverb to the generated output. Makes the result feel like it exists in the same acoustic space as a reference.

Format-aware export. Beyond WAV/MP3: FLAC for lossless archival, OGG for game engines (Godot, Unity), split stems as a multi-track zip, stems in a DAW-ready folder structure with tempo/key metadata embedded as BWF markers.

7. Reference track conditioning

Style cloning from audio. Drop in a reference track — a song you love — and extract its style descriptor: approximate tempo, key, instrumentation, energy profile, production style. Use that as the basis for the style prompt rather than typing it. This is what Suno's "create in the style of" does loosely, but doing it properly with audio feature extraction (via librosa or essentia) would be more accurate and more controllable.

Melody extraction and transfer. Pull the melody from a reference track and use it as a hint for the generated song. "Make something that has the same melodic shape as this but in a different style." Ethically careful — you're extracting structure, not copying audio — but very powerful.

Timbral matching. Match the overall tonal character (brightness, warmth, presence) of a reference. Useful when you're scoring a project that already has some music and you need new cues to match sonically.

8. Intelligent prompt assistance

Prompt expansion. The user types "sad country song about leaving home" and the system expands it: suggests specific instrumentation, vocal characteristics, tempo range, key, reference artists in that subgenre. The expanded prompt gets more specific results.

Negative prompting. "Generate this, but NOT with a piano, NOT with autotune, NOT with a trap beat." ACEStep may support exclusion terms in the caption — worth testing.

Prompt memory across sessions. The system remembers what style prompts produced results the user starred, and starts suggesting similar language. A lightweight personal taste model.

Style vocabulary guide. An in-app reference showing the terminology ACEStep responds well to — genre names, production terms, instrument names, vocal descriptors. New users waste a lot of attempts discovering what language the model understands.

9. Ideas that are genuinely novel

These don't exist anywhere yet, and some of them are harder than they sound — but worth naming.

Emotional coherence scoring. After generating, run a small classifier that estimates how well the music's sonic mood matches the intended mood from the prompt. Flag mismatches: "you asked for melancholy but this reads as angry — regenerate?"

Narrative arc mode. For long-form content (a podcast intro, a game soundtrack, an album), generate a set of related pieces that share melodic DNA but evolve over time. The pieces would be variations on a theme rather than unrelated songs.

Live regeneration during playback. While the song is playing, the user adjusts sliders in real time and the system queues a new generation with those parameters, crossfading in when ready. The closest thing to live performance that AI music currently offers.

Collaborative co-writing mode. The AI writes a verse, the user edits it, the AI writes the chorus constrained by the user's verse, back and forth. The lyric generator already has the right structure for this — it just needs a turn-based UI.

Adaptive scoring for interactive media. The music responds to state changes in a game or interactive experience — branching based on tension level, looping a calm section until an event triggers, transitioning to a combat theme. This requires a small runtime engine, not just file generation, but it's a product no one has built accessibly.

Micro-expression editing. After generation, identify the emotional "peak moments" in the audio automatically (chorus hits, bridge resolution, final note) and let the user say "make this moment bigger" or "soften this" — triggering a targeted regional regeneration at that exact timestamp.